Example Pert Diagram

Below is a table of 10 tasks, their precedence requirements, and their times to complete.

Complete a Pert Diagram

| Task | Predecessors Tasks (Dependencies) | Time (Weeks) |
| --- | --- | --- |
| A | - | 3 |
| B | - | 5 |
| C | - | 7 |
| D | A | 8 |
| E | B | 5 |
| F | # C | 5 |
| G | E | 4 |
| H | F | 5 |
| I | D | 6 |
| J | G-H | 4 |

Use the following diagrammatical representation to complete the Pert Diagram, Some tasks are already labelled; you need to finish the Diagram

SD

ED

TL

3 wks

SD

ED

TL

wks

T  A

T

SD

ED

TL

5 wks

SD

ED

TL

wks

SD

ED

TL

wks

SD

ED

TL

7 wks

1 What is the critical Path?

2 How long is the expected project duration?

- What is the critical path?

- How long is the expected project duration