## Slide 1: 14.3 Scheduling
Camp III,
July 6
Camp II,
July 4
Camp I, July 1

## Slide 2: Where are we?
SPMP IEEE Std 1058
0. Front Matter
1. Introduction
2. Project Organization
3. Managerial Process
4. Technical Process
5. Work Elements, Schedule, Budget
  5.1 Work Breakdown Structure
  5.2 Dependencies between tasks
  5.3 Resource Requirements
  5. 4 Budget
  5.5 Schedule (Today’s lecture)
Optional Inclusions

## Slide 3: Outline
The last lecture dealt with Work Breakdown Structures
Today we focus on Dependencies and Scheduling
Estimating times for activities
Determining critical path and slack times
Determining project duration
Many heuristics and examples
  How to live with a given deadline
  Optimizing schedules
  Rearranging schedules

## Slide 4: Dependency Diagrams (Overview)
Dependency diagrams consist of 3 elements
Event (also called milestone): A significant occurrence in the life of a project.
Activity: Work required to move from one event to the next.
Span time ( also called duration or elapsed time): The actual calendar time required to complete an activity.
  Span time parameters: people’s availability, parallelizability of the activity, availability of nonpersonnel resources, ….
Dependency Diagram are drawn as a connected graph of nodes and arrows.
2 commonly used diagram notations to display dependency diagrams:
  1) Activity-on-the-arrow (Mealy automaton)
  2) Activity-in-the-node (Moore automaton)

## Slide 5: Why Dependency Diagrams?
Example:
  You are assigned a project consisting of 10 activities which take one week each to be completed.
  How long does the project take?
When projects have more than 15-20 activities, one cannot to compute the schedule in the head any more.
Dependency Diagrams are a formal notation to help in the construction and analysis of complex schedules

## Slide 6: 1) Activity-on-the-arrow Diagram Notation
A
B
t
Event (Milestone
or Deliverable)
Event (Milestone
or Deliverable)
Activity
T1 = 4 weeks
RAD
SDD
System Design
Span Time

## Slide 7: PERT
PERT is an activity-on-the-arrow notation
PERT = Program Evaluation and Review Technique
Developed in the 50s to plan the Polaris weapon system in the USA.
PERT allows to assign optimistic, pessimistic and most likely estimates for the span times of each activity.
You can then compute the probability to determine the likelihood that overall project duration will fall within specified limits.

## Slide 8: 2) Activity-in-the-node Diagram Notation
RAD
available
t = 0
System Design
t = 2 weeks
SDD
available
t = 0
Event (Milestone
or Deliverable)
Event (Milestone
or Deliverable)
Activity
A Node is either an event or an activity.
Distinction: Events have span time 0
A
tA = 0
B
tB = 0
C
tC = 0
Milestone boxes are often highlighted by double-lines

## Slide 9: Example of an Activity-in -the -Node Diagram
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
5 = 2

## Slide 10: What do we do with these diagrams?
Compute the project duration
Determine activities that are critical to ensure a timely delivery
Analyse the diagrams
  to find ways to shorten the project duration
  To find ways to do activities in parallel
2 techniques are used
  Forward pass (determine critical paths)
  Backward pass (determine slack time)

## Slide 11: Definitions: Critical Path and Slack Time4
Critical path:
  A sequence of activities that take the longest time to complete
  The length of the critical path(s) defines how long your project will take to complete.
Noncritical path:
  A sequence of activities that you can delay and still finish the project in the shortest time possible.
Slack time:
  The maximum amount of time that you can delay an activity and still finish your project in the shortest time possible.

## Slide 12: Example of a critical path
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
5 = 2
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
Critical path in bold face

## Slide 13: Definitions: Start and Finish Dates
Earliest start date:
  The earliest date you can start an activity
Earliest finish date:
  The earliest date you can finish an activity
Latest start date:
  The latest date you can start an activity and still finish the project in the shortest time.
Latest finish date:
  The latest date you can finish an activity and still finish the project in the shortest time.

## Slide 14: 2 Ways to Analyze Dependency Diagrams
Forward pass: Goal is the determination of critical paths
  Compute earliest start and finish dates for each activity
  Start at the beginning of the project and determine how fast you can complete the activites along each path until you reach the final project milestone.
Backward pass: Goal the determination of slack times
  Compute latest start and finish dates activity
  Start at the end of your project, figure out for each activity how late it can be started so that you still finish the project at the earliest possible date.
To compute start and finish times, we apply 2 rules
  Rule 1: After a node is finished, we can proceed to the next node(s) that is reachable via a transition from the current node.
  Rule 2: To start a node all nodes must be complete from which transitions to that node are possible.

## Slide 15: Forward Path Example
Activity Earliest Start(ES) Earliest Finish(EF)
Activity 3
tA = 1
Activity 4
tA = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
A1 Start of week 1 End of week 5
A2 Start of week 6 End of week 6
A3 Start of week 1 End of week 1
A5 Start of week 6 End of week 7
A4 Start of week 2 End of week 4
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Project Duration = 7

## Slide 16: Backward Path Example
Activity Latest Start(LS) Latest Finish(LF)
Activity 3
tA = 1
Activity 4
tA = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
A2 End of week 7
A3 End of week 2
A5 End of week 7
A1 End of week 5
A4 End of week 5
Activity 3
t3 = 1
Activity 4
t4 = 3
Activity 2
t2 = 1
Start of week 6
Project Duration = 7
Start of week 3
Start of week 1
Start of week 7
Start of week 2

## Slide 17: Computation of slack times
Slack time ST of an activity A:
  STA = LSA - ESA
  Subtract the earliest start date from the latest start date for each activity
Activity 3
tA = 1
Activity 4
tA = 3
Activity 2
t2 = 1
Start
t = 0
Activity 1
t1 = 5
End
t = 0
Activity5
t5 = 2
Activity 4
t4 = 3
Activity 2
t2 = 1
Activity
A1
A2
A3
A4
A5
Slack time
0
1
1
1
0
Slack times on the same path influence each other.
Example: When Activity 3 is delayed by one week, activity 4 slack time becomes zero weeks.
Example: STA4 = 3 - 2 = 1

## Slide 18: Path types in dependency graphs
Critical path: Any path in a dependency diagram, in which all activities have zero slack time.
Noncritical path: Any path with at least one activity that has a nonzero slack time.
Overcritical path: A path with at least one activity that has a negative slack time.
  Overcritical paths should be considered as serious warnings: Your plan contains unreal time estimates
Any dependency diagram with no fixed intermediate milestones has at least one critical path.
A project schedule with fixed intermediate milestones might have no critical path
  Example: The analysis review must be done 1 month after project start, the estimated time for all activities before the review is 3 weeks.

## Slide 19: Frequently used formats for dependency graphs
Milestone View (“Key-Events report”):
  A table that lists milestones and the dates on which you plan to reach them.
Activities View:
  A table that lists the activities and the dates on which you plan to start and end them
Gantt chart View:
  A graphical illustrating on a timeline when each activity will start, be performed and end.
Combined Gantt Chart and Milestone View:
  The Gantt Chart contains activities as well as milestones.

## Slide 20: Key-Events Report
Date Milestone
August 26 Project Kickoff (with Client)
October 16 Analysis Review
October 26 System Design Review
November 7 Internal Object Design Review
November 20 Project Review (with Client)
Nov 26 Internal Project Review
Dec 11 Acceptance Test (with Client)
Good for introduction of SPMP and high executive briefings

## Slide 21: Activities View
Date Project Phases
Jul 17-Aug 23 Preplanning Phase
Aug 26 - Sep 24 Project Planning
Sep 11-Oct 8 Requirements Analysis
Oct 9 - Oct 26 System Design
Oct 28-Nov 7 Object Design
Nov 8 - Nov 20 Implementation & Unit Testing
Nov 22 - Dec 4 System Integration Testing
Dec 4 - Dec 10 System Testing
Dec 11- Dec 18 Post-Mortem Phase
Good for SPMP Section 5.5 and during developer meetings

## Slide 22: Gantt Chart
Time (in weeks after start)
Activity 1
Activity 2
1
2
3
4
5
6
7
0
Activity 3
Activity 4
Activity 5
Easy to read

## Slide 23: Gantt Chart
Time (in weeks after start)
Activity 1
Activity 2
1
2
3
4
5
6
7
0
Activity 3
Activity 4
Activity 5
Project Start
Project Finish
with milestones
  Good for reviews.
Design Review

## Slide 24: Two Types of Gantt Charts
Person-Centered View
  To determine people‘s load
Activity-Centered View
  To identify teams working together on the same tasks
Time
Time
Joe
Mary
Toby
Clara
A1
A3
Joe, Toby
A1
A3
A1
A2
A3
Joe
A2
Clara, Toby, Joe
A3
Choose one view, stay with it. Usually base the view on the WBS structure
Managing Experienced Teams: Person-centered view
Managing Beginners: Activity oriented view

## Slide 25: Tools support for Establishing Schedules
Tool support for
  Graphical user interface for entering activity data
  Automatic computation of critical paths
  Multiple views (PERT, Gantt, table views) and switching between these views
Many products available. Examples
  Fast Track (Demo) (http://www.aecsoft.com/downloads/demo/downloads_listindex.asp?bhcp=1)
    Main view: Gantt Charts
  Microsoft Project (http://www.microsoft.com/office/project/default.asp)
    PERT Charts, Gantt Charts, combined Milestone/Gantt Charts
Tool use and training beyond the scope of this class

## Slide 26: What do we cover now?
How to develop an initial project schedule
How to shorten the project duration
Mistakes made during preparation of schedules
The danger of fudge factors
How to identify when a project goes off-track (actual project does not match the project plan).
How to become a good software project manager

## Slide 27: How to develop an Initial Project Schedule
Identify all your activities (reuse a template if possible)
Identify intermediate and final dates that must be met
  Assign milestones to these dates
Identify all activities and milestones outside your project that may affect your project’s schedule
Identify “depends on” relationships between all these identified activities
Draw a dependency diagram for all identified activities and relationships
Analyze the diagram to determine critical paths and slack times of noncritical paths.
Example: Establish a schedule for system integration testing

## Slide 28: Developing a Schedule for Integration Testing
Five Steps:
  1. Start with System Decomposition
  2. Determine your Integration Testing Strategy
  3. Determine the Dependency Diagram (UML Activity Diagram)
  4. Add Time Estimates
  5. Visualize the activities on a time scale: Gantt Chart
See Bruegge&Dutoit 2003, Chapter 9 Testing

## Slide 29: 1. Start with System Decomposition

## Slide 30: 2. Determine Your Integration Testing Strategy
Types of integration testing strategies
We choose sandwich testing. Why?
  It allows many parallel testing activities, possibly shortening testing time
Sandwich testing requires 3 layers
  Reformulate the system decomposition into 3 layers if necessary
Identification of the 3 layers and their components in our example
  Top layer: A
  Target layer: B, C, D
  Bottom layer: E, F, G

## Slide 31: Sandwich Testing
Sandwich testing combines parallel top-down and bottom-up integration testing
  Top-down testing tests the top layer incrementally with the components of the target layer
  Bottom-up testing tests the bottom layer incrementally with the components of the target layer
Modified sandwich testing is more thorough
  Individual layer tests
    Top layer test with stubs for target layer
    Target layer test with drivers and stubs replacing top and bottom layers
    Bottom layer test with a driver for the target layer
  Combined layer tests
    Top layer access the target layer
    Target layer accesses bottom layer

## Slide 32: 3. Determine the Dependency Diagram (Sandwich Testing , UML Activity Diagram)
Target layer components: B, C, D

## Slide 33: Dependency Diagram for a Modified Sandwich Testing Strategy

## Slide 34: 4. Add Time Estimates (PERT Chart)

## Slide 35: 5. Visualize your Schedule (Gantt Chart View )

## Slide 36: What do we cover now?
How to develop an initial project schedule
How to shorten the project duration
Mistakes made during preparation of schedules
The danger of fudge factors
How to identify when a project goes off-track (actual project does not match the project plan).
How to become a better software project manager

## Slide 37: How to reduce the planned project time
Recheck the original span time estimates
  Ask other experts to check the estimates
  Has the development environment changed? (batch vs interactive systems, desktop vs laptop development)
Hire more experienced personnel to perform the activities
  Trade-off: Experts work fast, but cost more
Consider different strategies to perform the activities
  Consider to Buy a work product instead of building it (Trade-off: Buy-vs-build)
  Consider extern subcontractor instead of performing the work work internally
Try to find parallelizable activites on the critical path
  Continue coding while waiting for the results of a review
  Risky activity, portions of the work may have to be redone.
Develop an entirely new strategy to solve the problem

## Slide 38: Typical Mistakes when Developing Schedules
The „Backing in“ Mistake
Using Fudge Factors

## Slide 39: The “Backing in” Mistake
Definition “Backing In”:
  You start at the last milestone of the project and work your way back toward the starting milestone, while estimating durations that will add up to the amount of the available time
Problems with Backing in:
  You probably miss activities because your focus is on meeting the time constraints rather than identifying the required work
  Your span time estimates are based on what you allow activites to take, not what they actually require
  The order in which you propose activities may not be the most effective one.
Instead, start with computing all the required times and then try to shorten the project duration

## Slide 40: Using Fudge Factors
Parkinson formulated this law for project completion:
  Work tends to expand to fill the time allotted for it.
Fudge factor:
  A fudge factor is the extra amount of time you add to your best estimate of span time “just to be safe”.
  Example: Many software companies double their span time estimates.
Don’t use fudge factors because of Parkinson’s law.
  If an activity takes 2 weeks, but you add a 50% fudge factor, chances are almost zero that it will be done in less then 3 weeks.

## Slide 41: Heuristics for dealing with time
1. First Set the Project Start Time =>
  Determines the planned project time
  Determine the critical path(s)
2. Then try to reduce the planned project time
  If you want to get your project done in less time, you need to consider ways to shorten the aggregate time it takes to complete the critical path.
Avoid fudge factors

## Slide 42: Identifying When a Project Goes Off-Track
Determine what went wrong: Why is your project got off track?
  Behind schedule
  Overspending of resource budgets
  Not producing the desired deliverables
Identify the Reason(s):
  You are new on the job, this is your first project, and you made mistakes
  Key people left the teams or new ones are joining it
  Key people lost interest or new ones entered the picture
  The requirements have changed
  New technology has emerged
  The business objectives have changed
  Organizational priorities have shifted (for example after a merger)

## Slide 43: Heuristics to get a project back on track
Reaffirm your plan
  Reaffirm your key people
  Reaffirm your project objectives
  Reaffirm the activities remaining to be done
  Reaffirm roles and responsibilities (Lecture on Project organization, May 7))
Refocus team direction and commitment
  Revise estimates, develop a viable schedule
  Modify your personnel assignments (May 7)
  Hold a midproject kickoff session
  Closely monitor and control performance for the remainder of the project (Lecture on Project Controlling, June 25)
Get practical experience

## Slide 44: What makes a Software Project successful?
User involvement 20
Support from upper management 15
Clear Business Objectives 15
Experienced Project Manager 15
Shorter project phases („Small milestones“) 10
Firm core requirements („basic requirements“) 5
Competent Staff 5
Proper Planning 5
Ownership 5
Other 5
100 %
From Standish Group http://www.standishgroup.com/sample_research/chaos1998.pdf

## Slide 45: Become a better software project manager
End User and Management involvement 35%
  Learn how to involve the customer and end users
  Learn how to get support from your upper management
Practice project management 30 %
  Do as many projects as possible
  Learn from your project failures
Focus on business objectives and requirements 20%
  Distinguish between core, optional and fancy requirements

## Slide 46: How to become a better project manager
Don’t assume anything
  Take the time to find out the facts.
  Use assumptions only as a last resort.
  With every assumption comes a risk that you are wrong.
Communicate clearly with your people.
  Being vague does not get your more leeway, it just increases the chances for misunderstanding.
Acknowledge good performance
  Tell the person, the person’s boss, team members, peers.
View your people as allies not as adversaries
  Focus on common goals, not on individual agendas.
  Make people comfortable by encouraging brainstorming and creative thinking
Be a manager and a leader
  Deal with people as well as to deliverables, processes and systems.
  Create a sense of vision and excitement.

## Slide 47: Additional Readings
[IEEE Std 1058] Standard for Software Project Management Plans
Stanley E Portny, Project Management for Dummies, Hungry Minds, 2001, ISBN 0-7645-5283-X
Standish Group: Chaos, Sample Research Paper, 1998 http://www.standishgroup.com/sample_research/chaos1998.pdf
[Royse 1998], Software Project Management, Addison-Wesley, ISBN0-201-30958-0

## Slide 48: Summary
Software Project Management Plan, Section 5:
    5.1 Work Breakdown Structure
    5.2 Dependencies between tasks
    5.3 Resource Requirements (=> Lecture on project organization)
    5. 4 Budget (=> Lecture on project estimation)
    5.5 Schedule
Work Breakdown Structure (WBS): Set of activities to do (“use cases”)
Dependency Graph: Identification of dependency relationships between activities identified in the WBS
Schedule: Dependency graph decorated with time estimates for each activity
PERT: One of the first techniques proposed to analyse complex dependency graphs and schedules
Gantt Chart: Simple notation used to visualize a schedule

## Slide 49: Summary: Another view:-)
Developing a project plan is is an art. Practice it!
Use project templates for yourself or your organization, build these templates iteratively
There are several different ways to do a WBS (activity-oriented, entity-oriented, ….)
The detailed planning horizon should not got beyond a 3 month time frame
Innovative projects with changing requirements or technology enablers should include a initial planning phase that results in a project agreement.
A dependency graph is the WBS plus dependencies.
A schedule is a dependency graph plus time estimates
Budget should not be specified before the work is clear:
  If the preplanning phase needs a budget, ask for a separate budget