## Slide 1
Diagram 1: Pert chart of first 9 months of PhD postgraduate study
1
0
1
2
0
2
M1
0
4
4
5
2
0
3
6
7
6
0
5
8
9
8
0
6
6
6
8
0
4
6
6
4
0
7
14
15
3
0
8
18
19
Start
ES=0
LS=0
LT=7
ET=6
M2
LT=22
ET=21
2
0
9
21
22
2
0
10
23
24
4
0
11
25
26
2
0
12
29
30
4
0
13
29
30
M3
EF=33
LF=34
Earliest start
Latest start
Task Number
Duration
Float
Milestones
ES = Earliest start time, LS = Latest start time, ET = Earliest time milestone, LT = Latest time milestone, EF = Earliest finish time project, LF = Latest finish time project.
Legend for PERT chart